## Sheet1
Rail Systems Mains Access Options
Option | Description | Pros | Cons | RS Construction Scope | Compound Impact | Possession Impact | Delivery Impact | Mitigations to meet programme
1) Do Nothing | Access from Jacob's Ladder/Southall | Ready to use today | Over 10km travel to site of work |  | No additional compound space, large works delivered from NPD (where possible) or Southall | Loss of efficiency in possession access of 25% | Delays in OLE works due to less efficeint working mean Xmas 2026 configuration change cannot be met, delay in programme of 1 year, Configuration state changes move to Xmas 2027 & 2029, programme complete Xmas 2030 | Agree mid-year blockades & disruptive possession regime through summer timetable 2025 & 2026 Probability: Very Low
| Access from NPD at start & end of disruptive possessions | No costs associated | No use of NPD RRAP for majority of possession, significant risk assocated with plant breakdown, emergeny access |  |  | Increase in isolation costs due to extended iso footprint of 50% of all mains blocks. Greater level of disruption to TOCs |  | Agree block of NPD access throughout possession, NPD trains stabled elsewhere Probability: Very Low
2) New RRAP at Jewson's | New temporary construction compound & RRAP at Jewson's Yard | Falls within all isolation footprints | Land agreements not agreed | RRAP and Compound to be built ahead of January 2025 at latest, would require accelerated process if land handed over later than September '24 as planned | Ample storage space to deliver works efficiently, material brought to site ahead of possession |  | No impact to programme if RRAP can be utilised from January 2025 | Agree land purchase to build compound from mid-2024 Probabilty: Average
| New permanent maintenance RRAP | Compound space & low set-up costs | Proximity to local residents
Easy access from road to track
3) New RRAP at OOC Lane | Access through Hitachi Depot via OOC Lane, some level of disruption to depot operations required | Falls within all isolation footprints | Significant interface & risk associated between live depot and construction works | Accelerate constuction of access currently proposed for Xmas 2026 by 2 years, responsibility for construction TBC (currently BBVS) | Limited compound space available pre-2027, just in time delivery. If access road is not available, plant would need to be offloaded directly on public highway OOC Lane | Loss in efficiency in possession access of 10% (if access road not constructed) due to constrained access | No impact to programme if RRAP can be utilised from January 2025 | Agree handover date with BBVS of Land in Wormwood Scrubs for access from mid-2024 Probability: Low Alternative, agree road access with Hitachi through depot from East access Probability: Very Low
| Re-configured access road in Wormwood Scrubs | Access required already post-Xmas 2026 | Land in Wormwood Scrubs may not be ready for 2024 | Land required for access may not be available as currently in use for thrust-bore UTX work |  |  |  | Agree interface between HS2 works and depot operations between 2025-2029 Probability: Low
4) New RRAP at Horn Lane | New RRAP at Friary Road off Horn Lane | Falls within all isolation footprints | Significant works due to level difference between roadway and rail | New RRAP constructed at cost of £20,000,000 - complex location | Limited to no compound space available, just in time delivery. |  | No impact to programme if RRAP can be utilised from January 2025 | Permission to remove multiple trees under TPO & highway modifications Probability: High
No compound/storage space
|  |  | Land agreements may not be achievable (at least within required timescales) | Construction programme of 1 year |  |  |  | Permission to create new access road directly adjacent to new build properties: Probability: Low ...in time for Jan 2025 Probability: Very Low
5) New RRAP at Bloomsbury Close | New RRAP at Bloomsbury Close | Relelative flat access from road level to track | Does not fall within extended block isolation footprint & further from site of works | New RRAP constructed at cost of £10,000,000 | Some compound space may be available, dependant on the purchase of private garages | Loss in efficiency in possession access of 10% due to travel distance from site |  | Permission to remove multiple trees under TPO Probability: High
|  | Sufficient space track-side | Road route to access may not prove sufficient |  |  |  |  | Permission to create new access road directly adjacent to new build properties: Probability: Low ...in time for Jan 2025 Probability: Very Low
|  |  | Works may require purchase of private garages | Construction programme of 10 months |  | Increase in isolation costs due to extended iso footprint of 50% of all mains blocks. Greater level of disruption to TOCs |  | All mains lead possessions/isolations to extend close to Hangar Lane Probability: High
Land agreements may not be achievable (at least within required timescales)