## Sheet1
OOC Lane/Hitachi Access Point Requirements Matrix
| Mains Track Access | Southern Brownfield
Dates | July 2024 - December 2026 | Christmas 2026 - Christmas 2028
Usage | Rail Access for SRSA in mainly Weekend possession hours | Midweek access for SRSA and BBVS to brownfield site
Ramp | Construction of new ramp by BBVS will occur during works programme, needs to be undertaken in summer to avoid impacting disruptive possessions. HS2 to confirm programme | Required ahead of start of works Explore SRSA support in ramp construction to meet programme
Vehicles | Only smaller plant able to access via existing ramp (RRVs, MEWPs). Vehicle pathing analysis to be completed. Larger plant/materials to access on ad-hoc basis from Eastern access. Route requires validation & agreement with Hitachi. | All plant to access from OOC Lane, including HGVs and dumpers
OOC Lane | Area needed in HS2 Wormwood Scrubs compound to facilitate storage & off-loading of machine deliveries. HS2 to confirm timetable of works to provide available access. If area of Wormword Scrubs compound cannot be provided, agreement would be needed with local authorities to off-load machines directly onto OOC Lane. | HGV routes from OOC Lane need to be approved by HS2
Compound | Laydown areas required within Wormwood Scrubs depot and adjacent to RRAP within Hitachi depot | Area required within Hitachi depot and in OOC Station brownfield site
Level Crossing | Level crossing panels require replacement & upgrades to safety protection around crossing Crossing to remain live at all time, bespoke procedure for travelling under live required Risk Hitachi train block access to possessions by parking across level crossing | Level crossing panels require replacement & upgrades to safety protection around crossing Crossing to remain live at all time, bespoke procedure for travelling under live required
Hitachi | Agreement require for additional, early access above previous discussions Agreement needed on interface between Hitachi staff/vehicle movements & OOC station works | Agreement needed on interface between Hitachi staff/vehicle movements & OOC station works
RRAP | Survey & design required to confirm feasibility of RRAP at OOC Lane. Risk that track cant and level difference make it unsuitable location | Proposal for RRAP to be installed on new track alignment with access through OOC Station brownfield site