## Rates
Rates
Permanent Land Take
Pasture Land | 20000 | per acre
Verges, trees and embankments | 4000 | per acre
Roads and paths | 5000 | per acre
Rates agreed as per John Sawdon Email of 12/7/24.
Temporary Land Take | Tom Vacher confirmed on 25/10/23 that they had no instruction regarding the Temporary land requirement

## Acquisition Schedule
Land Reference No | Acquisition Type | Ownership Reference Number | Area (Sqm) | Acres | Nature | Operational/ non-operational / Part Operational | NH Response
1-005 | Powers of Temporary Use of Land | 305 | 248.3793 | 0.061376 | Freeholder | Non-operational | No Objection
1-006 | Unrestricted Powers to Acquire Land | 310 | 6.406 | 0.001583 | Freeholder | Non-operational | No Objection
1-007 | Powers to Operate | 310 | 31.9788 | 0.0079021 | Freeholder | Non-operational | No Objection
1-008 | Powers to Operate | 330 | 215.3605 | 0.053217 | Freeholder | Non-operational | No Objection
1-009 | Powers of Temporary Use of Land | 340 | 0.76896 | 0.00019001 | Freeholder | Non-operational | No Objection
1-010 | Unrestricted Powers to Acquire Land | 340 | 67.3469 | 0.016642 | Freeholder | Non-operational | No Objection
1-011 | Unrestricted Powers to Acquire Land | 1615 | 709.4732 | 0.17531 | Freeholder | Non-operational | No Objection
1-012 | Unrestricted Powers to Acquire Land | 1720 | 108.25 | 0.026749 | Freeholder | Non-operational | No Objection
1-013 | Powers of Temporary Use of Land | 330 | 339.0226 | 0.083774 | Freeholder | Non-operational | No Objection
1-014 | Powers of Temporary Use of Land | 1720 | 920.1549 | 0.22738 | Freeholder | Non-operational | No Objection
1-016 | Unrestricted Powers to Acquire Land | 1715 | 14.0029 | 0.0034602 | Freeholder | Non-operational | No Objection
1-017 | Powers of Temporary Use of Land | 1715 | 256.5265 | 0.063389 | Freeholder | Non-operational | No Objection
1-023 | Powers of Temporary Use of Land | 1715 | 569.3402 | 0.14069 | Freeholder | Non-operational | No Objection
1-025 | Powers of Temporary Use of Land and Acquisition of Permanent Rights | 1715 | 103.6094 | 0.025602 | Freeholder | Non-operational | No Objection
1-026 | Powers of Temporary Use of Land | 340 | 0.42472 | 0.00010495 | Freeholder | Non-operational | No Objection
1-027 | Powers of Temporary Use of Land and Acquisition of Permanent Rights | 340 | 13.8672 | 0.0034267 | Freeholder | Non-operational | No Objection
1-029 | Powers of Temporary Use of Land | 340 | 19.3771 | 0.0047882 | Freeholder | Non-operational | No Objection
10-109 | Unrestricted Powers to Acquire Land | 1730 | 945.8059 | 0.23371 | Freeholder | Non-operational | No Objection
10-115 | Unrestricted Powers to Acquire Land | 1030 | 80.2666 | 0.019834 | Freeholder | Non-operational | No Objection
14-149 | Powers of Temporary Use of Land | 1395 | 3172.8529 | 0.78403 | Freeholder | Operational | No Objection subject to DLOA
14-150 | Powers Air Rights | 1395 | 4590.0239 | 1.1342 | Freeholder | Operational | Agreed subject to Protective Provisions
14-151 | Powers of Temporary Use of Land | 1395 | 631.2638 | 0.15599 | Freeholder | Operational | No Objection subject to DLOA
14-152 | Unrestricted Powers to Acquire Land | 1665 | 284.4927 | 0.0703 | Freeholder | Part Operational | Objection - protective provision paragraph 96
2-031 | Unrestricted Powers to Acquire Land | 370 | 3359.3242 | 0.83011 | Freeholder | Part Operational | Objection - protective provision paragraph 96
3-035 | Unrestricted Powers to Acquire Land | 370 | 909.07 | 0.22464 | Freeholder | Operational | No Objection
3-037 | Powers of Temporary Use of Land | 410 | 3432.7752 | 0.84826 | Freeholder | Operational | Protective provision relating to construction of retaining feature. Road space and traffic management restrictions for SRN A428
3-038 | Unrestricted Powers to Acquire Land | 410 | 11598.6497 | 2.8661 | Freeholder | Part Operational | Objection - protective provision paragraph 96
4-040 | Powers of Temporary Use of Land | 370 | 245.0137 | 0.060544 | Freeholder | Part Operational | No Objection Local authority road verge
4-041a | Powers of Temporary Use of Land | 410 | 198.9045 | 0.04915 | Freeholder | Non-operational | No Objection
4-041b | Powers of Temporary Use of Land | 410 | 1478.7511 | 0.36541 | Freeholder | Non-operational | No Objection
4-042 | Powers of Temporary Use of Land | 365 | 41.0363 | 0.01014 | Freeholder | Non-operational | No Objection
4-044 | Unrestricted Powers to Acquire Land | 365 | 14.1023 | 0.0034848 | Freeholder | Non-operational | No Objection
4-045 | Powers of Temporary Use of Land | 365 | 90.8719 | 0.022455 | Freeholder | Non-operational | No Objection
4-046 | Powers of Temporary Use of Land | 410 | 419.084 | 0.10356 | Freeholder | Non-operational | No Objection
4-052 | Unrestricted Powers to Acquire Land | 850 | 31918.9495 | 7.8873 | Freeholder | Part Operational | Objection - protective provision paragraph 96
4-053 | Powers of Temporary Use of Land | 850 | 24932.9225 | 6.1611 | Freeholder | Operational | Objection - protective provision paragraph 96
5-054 | Unrestricted Powers to Acquire Land | 850 | 10949.4977 | 2.7057 | Freeholder | Part Operational | Objection - protective provision paragraph 96
5-055 | Unrestricted Powers to Acquire Land | 435 | 329.0543 | 0.081311 | Freeholder | Non-operational | No Objection
5-056 | Unrestricted Powers to Acquire Land | 1745 | 80.3937 | 0.019866 | Freeholder | Non-operational | No Objection
5-058 | Powers of Temporary Use of Land | 1625 | 43342.6593 | 10.7102 | Freeholder | Non-operational | No Objection
5-059 | Powers of Temporary Use of Land | 435 | 2516.8611 | 0.62193 | Freeholder | Non-operational | No Objection
5-060 | Unrestricted Powers to Acquire Land | 435 | 8263.933 | 2.0421 | Freeholder | Non-operational | No Objection
5-063 | Unrestricted Powers to Acquire Land | 1625 | 69.3138 | 0.017128 | Freeholder | Non-operational | No Objection
5-064 | Powers of Temporary Use of Land | 435 | 2088.3303 | 0.51604 | Freeholder | Non-operational | No Objection
5-065 | Unrestricted Powers to Acquire Land | 850 | 184.3565 | 0.045555 | Freeholder | Operational | No Objection due to being plot on LHA road side
5-066 | Powers of Temporary Use of Land | 435 | 844.9527 | 0.20879 | Freeholder | Part Operational | No Objection
5-067 | Powers of Temporary Use of Land | 470 | 6310.1586 | 1.5593 | Freeholder | Non-operational | No Objection
6-068 | Powers of Temporary Use of Land | 545 | 40.8318 | 0.01009 | Freeholder | Non-operational | No Objection
6-069 | Powers of Temporary Use of Land | 545 | 303.3831 | 0.074968 | Freeholder | Part Operational | No Objection subject to DLOA
6-070 | Powers of Temporary Use of Land | 850 | 174.7457 | 0.043181 | Freeholder | Operational | No Objection subject to DLOA
6-071 | Powers of Temporary Use of Land | 470 | 22.1461 | 0.0054724 | Freeholder | Operational | No Objection subject to DLOA
6-072 | Unrestricted Powers to Acquire Land | 850 | 1105.4086 | 0.27315 | Freeholder | Part Operational | No Objection subject to DLOA
6-074 | Unrestricted Powers to Acquire Land | 850 | 1135.7916 | 0.28066 | Freeholder | Operational | No Objection
6-079 | Unrestricted Powers to Acquire Land | 655 | 196.4839 | 0.048552 | Freeholder | Non-operational | No Objection
6-080 | Unrestricted Powers to Acquire Land | 850 | 472.6592 | 0.1168 | Freeholder | Operational | No Objection
8-082 | Powers of Temporary Use of Land | 840 | 67.869 | 0.016771 | Freeholder | Operational | No Objection
9-092 | Powers of Temporary Use of Land | 1625 | 2255.3824 | 0.55732 | Freeholder | Operational | No Objection subject to DLOA
9-095 | Powers of Temporary Use of Land | 1070 | 124.2907 | 0.030713 | Freeholder | Operational | Note from WSP to AR email 19/12/24 extent of land required is going to be less for construction, however land purchase will remain for TWAO.
9-085a | Unrestricted Powers to Acquire Land | 1625 | 3172.23 | 0.78387 | Freeholder | Operational
9-085b | Unrestricted Powers to Acquire Land | 1625 | 2810.36 | 0.69445 | Freeholder | Non-operational | No Objection
9-085c | Unrestricted Powers to Acquire Land | 1625 | 7127.62 | 1.7613 | Freeholder | Part Operational | Objection - protective provision paragraph 96
9-096 | Unrestricted Powers to Acquire Land | 1070 | 1249.9464 | 0.30887 | Freeholder | Operational | Objection - protective provision paragraph 96
9-099 | Unrestricted Powers to Acquire Land | 1000 | 79.0944 | 0.019545 | Freeholder | Non-operational | No Objection
|  |  | 187286.2039 | 46.2794