## Sheet1
Access | Track Bias | Mileage | Current RRAP Status | RS Use | RS Dates | Works Required | Works Criticality | Pros | Cons | RS Use Key
Jacob's Ladder | Mains | 6m63ch | In Use | Occasional RS Access | May 2023-Until Jewsons Operational | Minor Compound/RRAP Upgrade Works | Low | Critical for mains access in 2023 due to lack of other available access points | ~3miles for site of work | Occasional RS Access | Track access < 1 in 4 weekend
[9 empty] | Outside of standard isolation limits | Possession Mobilisation Compound | Compound for weekend possessions >2000m2 of laydown area & 650m2 for RRV stabling
[9 empty] | Busy & constrained access (via Waitrose) | Distribution Hub | Primary centre for external material deliveres, storage and fabrication - >12000m2 overall
[9 empty] | Funding source for upgrade works not confirmed | Maintenance Access | Small plant access for general track maintenance, Not required for RS
Acton Yard (Sand Road) | Reliefs (via Poplars) | 4m70ch | In Use (To be Modified) | Occasional RS Access | May 2023-2028 | New longer RRAP installed, new mobilisation compound and access road modifications | Medium | Space available | Not always within possession/isolation footprint | Primary RS Access | Track access for RS every mains or reliefs possession
OPTION 1 (PREFERRED) |  |  |  | Possession Mobilisation Compound |  |  |  | Proximity to Ealing Headspan works | Requires land purchase | Primary Brownfield Access | Access across Hitatchi Depot for work in rail locked site - >100 vehicle movements at maximum
[8 empty] | Provides redundancy to reliefs, efficiencies in programme | Suboptimal road access
Acton Yard (Sand Road) | Reliefs (via Poplars) | 4m70ch | In Use (To be Modified) | Occasional RS Access | May 2023-2028 | Major groundworks, highway works and compound establishment | Low | Proximity to Ealing Headspan works | High mobilisation costs
OPTION 2 |  |  |  | Distribution Hub |  | New longer RRAP installed |  | Provides redundancy to reliefs access & efficiencies in programme | Complex 3rd party interfaces
Not always within possession/isolation footprint
Requires land purchase
Suboptimal road access
Jewson's Yard (Permanent) | Mains | 4m28ch | Proposed | Maintenance Access | Post 2028 | New compound, RRAP, UTX and OLE relocations | Low | Currently limited mains access in this location | Requires land purchase
Significant De-veg and prep works
RRAP on DEP boundary
Constrained compound & access
Jewson's Yard (Temporary) | Mains | 4m23ch | Proposed | Primary RS Access | mid 2025-2028 | Modify existing yard, new RRAP, cable works | High | Currently limited mains access in this location | Requires land purchase
|  |  |  | Possession Mobilisation Compound |  |  |  | Existing large yard can modified | Works required on compound-RRAP interface
RRAP may not be opertational for requried start date
Constrained with Acton ML platform (solution believed to be achievable)
OOC Station RRAP (Phase 2) | Reliefs | 3m45ch | Proposed | Primary RS Access | Jan 2024 - March 2025 | New RRAP | Low | Close to site of works | Access via HS2 Haul Road
[8 empty] | May be opportunity to value engineer RRAP out of proposal | Only in use for short period of time
OOC Station RRAP (Phase 3 - Permanent) | Reliefs | 3m41ch | Proposed | Primary RS Access | April 2025 - 2028 | New RRAP & Compound | Medium | Close to site of works | RRAP requires relocations for temporary and permanent track alignments
(Maintenance access route post 2028 excluded from scope)
OOC Station RRAP (Phase 1) | Reliefs | 3m25ch | In Use | Primary RS Access | In Use until Xmas 2025 | None | Low | Existing Access | Interface with track works as these are built around it
Close to site of works
North Pole Depot | Mains | 3m35ch | Proposed | Primary Brownfield Access | (Xmas 2026 - Xmas 2028) | New RRAP, dewiring works, compound, access road & vehicle storage | High | Provides only source of off-track access to brownfield site | Significant prep works required
(OOC Lane) | [8 empty] | Significant impact/interface with North Pole Operations
Requires land purchase/agreement
Eastern Compound | Reliefs | 2m63ch | Proposed | Maintenace Occasional RS Access | Post 2028 Benefit from Jan 2027 | New RRAP, compound and access ramp | Medium | Provides alternative reliefs access opportunity if accelerated | Access via HS2 site
RRAP would require relocation from temporary to permanent alignment
North Pole Depot | Mains | 1m73ch | In Use (To be Modified) | Primary RS Access | May 2023-2028 | New RRAP direct onto mains, establish primary compound and utilities connections | High | Provides low mileage access | Requires land purchase, available land area TBC, may conflict with 3rd parties
(Mitre Way) |  |  |  | Distribution Hub |  |  |  | Uses existing compound
OPTION 1 (PREFERRED) |  |  |  | (2023-2028) |  |  |  | Efficiencies in using existing shed, low mobilisation costs
North Pole Depot | Mains | 1m73ch | In Use (To be Modified) | Primary RS Access | May 2023-2028 | New RRAP direct onto mains, mobilisation compound | Medium | Provides low mileage access | Requires land purchase
(Mitre Way) |  |  |  | (2023-2028) |  |  |  | Uses existing compound
OPTION 2